## Slide 1: Project Update
ROSE BOWL RENOVATION AND IMPROVEMENT PROJECT
City Council Meeting
May 20, 2013

## Slide 2: Project Update
2
Pavilion Substantial Completion; April 15
Premium seating sales: $5.3 million

## Slide 3
3
  Work in progress
    West side restrooms
    North electrical substation
    Broadcast building
    Permanent broadcast cabling
    Pavilion signage
Project Update

## Slide 4
4
  Local Hire Efforts
    226 Pasadena Residents hired on the project
    $2,182,827 has been paid to residents (10.4%)
    $9,808,499 has been paid to local vendors through
    local subcontracting, local vendors, and local procurement
Project Update

## Slide 5
5
Description of Sources | Funds Available as of 4/24/13 | Anticipated Funds through 2013 | Anticipated Funds through 2018
2010 Bond Proceeds | 126.1 M |  | 
2010 BCS Revenue (RBOC) | 2.0 M |  | 
2006/2010 BCS (TOR) | 4.0 M |  | 
RBOC/IMG Retained Earnings | 1.1 M |  | 
Capital User Fee (TOR) | 1.6 M |  | 
2013 Bond Restructure Proceeds | 30.0 M |  | 
2010 Bond Interest |  | 0.4 M 1 | 
Concessionaire Investment |  | 2.0 M | 
2014 BCS Revenue |  |  | 3.4 M 2
Brick Campaign |  |  | 2.0 M 3
Legacy Contribution |  | 2.0 M | 7.0 M
Totals | $164.8 M | $169.2 M | $181.6 M

## Slide 6: Updated Estimated Project Costs through 2014 (in millions)
6
Description | Awarded/Committed Costs + Estimated Costs 2014
Awarded/Committed Cost through Dec 2013 | 156.6 M
Estimated Direct Construction Cost (estimated to occur in 2014) | 9.02 M
Estimated Indirect Construction Costs (estimated to occur in 2014) | 1.1 M
Estimated Soft Costs, including FFE (estimated to occur in 2014) | 1.47 M
Sub-total through Dec 2014 | $168.8 M
Estimated Future Work (pending funding) | $12.7 M
Estimated Project Total through Dec 2018 | $181.5 M
Refer Project Uses of Funds dated 4/24/13;
(Prior Attachment C- Project Sources dated 12/31/12 has been included for reference)

## Slide 7
7
2014 Work and Implementation
    Field work for exiting purposes
    Restrooms field level
    Gate A improvements
    Bio-swale
    South end electrical substation
    Meter consolidation
Project Update

## Slide 8
8
Remaining project elements (2015-2018)
    Upgrade 7 remaining gates
    Expand course area
    Increase concessions points of sale
    Transfer 17KV electrical service to existing structures
Project Update

## Slide 9: Legacy Update
ROSE BOWL RENOVATION AND IMPROVEMENT PROJECT

## Slide 10
10
Legacy Update
Primary purpose to raise funds for Rose Bowl renovation project
Operating agreement with City & RBOC; Delegates to RBOC the authority to manage the naming rights
Tonight RBOC is requesting:
  Overall approval to name all inventory within fence line
    Will return to Council if field naming is seriously considered
  Provide Legacy opportunity to name Parkway & Area H
  Conceptual approval for Donor Plaza and Court of Champions

## Slide 11
11
15 Current Board members
Legacy pledges approx. $10 million to date
  7 year pledge period
  $2 million for project by the end of 2013
Legacy goal: $20 million (net)
  Terry Donahue pavilion
  Stadium Naming opportunities
  Court of Champions
  Public Campaign–Donor Plaza
  Areas leading into stadium – Parkway & Area H
Legacy Update

## Slide 12: Public Campaign – Donor Plaza
12

## Slide 13: Court of Champions
13

## Slide 15
AREA H
PARKWAY